# Pilot status report

Prepared on 2 October 2026 by the project office.

# Sumary

The pilot started in September with ten participants across two sites.

Feedback so far is positive, and the team expects to finish on schedule.

- Site visits are complete

- Training material is in review

- Reporting starts next month

# Budget

The table lists planned and actual costs in euros.

| Item | Owner | Planned | Actual |
| --- | --- | --- | --- |
| Rent | Avery | 300 | 320 |
| Supplies | Robin | 120 | 100 |
| Travel | Morgan | 200 | 210 |
| Total |  | 620 | 630 |

# Next steps

Collect the remaining feedback forms.

Prepare the final report for the steering group.