## Sheet2
Count of Overdue/On Time | Column Labels
Row Labels | OD | OT | Grand Total
2016-11-03 |  | 3 | 3
2016-11-04 | 2 | 1 | 3
2016-11-05 | 5 | 12 | 17
2016-11-06 | 3 | 6 | 9
2016-11-07 | 23 | 2 | 25
2016-11-08 | 8 | 7 | 15
2016-11-09 | 9 | 10 | 19
2016-11-10 | 9 | 4 | 13
2016-11-11 | 3 | 7 | 10
2016-11-13 | 3 | 1 | 4
2016-11-14 | 20 | 5 | 25
2016-11-15 | 5 | 6 | 11
2016-11-16 | 12 | 6 | 18
2016-11-17 | 10 | 2 | 12
2016-11-18 |  | 12 | 12
2016-11-19 | 2 |  | 2
2016-11-20 | 6 |  | 6
2016-11-21 | 3 | 7 | 10
2016-11-22 |  | 20 | 20
2016-11-23 | 10 | 10 | 20
2016-11-24 | 12 | 1 | 13
2016-11-25 | 8 |  | 8
2016-11-26 |  | 1 | 1
2016-11-27 | 2 |  | 2
2016-11-28 | 11 |  | 11
2016-11-29 |  | 1 | 1
2016-11-30 |  | 13 | 13
2016-12-01 |  | 1 | 1
2016-12-12 |  | 1 | 1
2016-12-15 |  | 1 | 1
Grand Total | 166 | 140 | 306

## Sheet1
Work Order | Equipment Description | Work Order Description | Type | Status | Reported By | Date Created | Sched. Start Date | Sched. End Date | Date Completed | Column1 | Overdue/On Time | Week Closed | Qty open in current wk
1 | m/c 1 | Transducer Calibration Annual Service | Preventive Maintenance | Completed | L114 | 2016-04-26 | 2016-12-15 | 2016-12-28 | 2016-08-08
2 | m/c 2 | Moulding Tool 1 | Preventive Maintenance | Completed | L112 | 2016-11-25 | 2016-12-12 | 2016-12-25 | 2016-11-25
3 | m/c 3 | Head clean Line 1 | Other | Completed | L110 | 2016-12-01 | 2016-12-01 | 2016-12-08 | 2016-12-01
4 | m/c 4 | tool change prep | Unplanned | Completed | L108 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
5 | m/c 1 | setpoints defaulted had to setup again. | Unplanned | Completed | L108 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
6 | m/c 2 | slider strip down remove rebuild. | Unplanned | Completed | L108 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
7 | m/c 3 | Moulding Tool 1 | Unplanned | Completed | L108 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
8 | m/c 4 | Moulding Tool 2 | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
9 | m/c 1 | Moulding Tool 3 | Administrative | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
10 | m/c 1 | Head clean Line 1 | Improvement | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
11 | m/c 2 | tool change prep | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
12 | m/c 3 | setpoints defaulted had to setup again. | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
13 | m/c 4 | M/c start | Administrative | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
14 | m/c 2 | Needle temperature | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
15 | m/c 3 | Will not start m/c 1 | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
16 | m/c 4 | rewire sensors | Unplanned | Completed | L108 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
17 | m/c 5 | grinder stopped | Unplanned | Completed | L108 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29
18 | m/c 6 | force welding not reached | Unplanned | Completed | L108 | 2016-11-29 | 2016-11-28 | 2016-11-28 | 2016-11-29
19 | m/c 7 | grinder stopped interlock not made. | Unplanned | Completed | L108 | 2016-11-29 | 2016-11-28 | 2016-11-28 | 2016-11-29
20 | m/c 2 | tool change prep | Unplanned | Completed | L108 | 2016-11-29 | 2016-11-28 | 2016-11-28 | 2016-11-29
21 | m/c 3 | laser problems | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
22 | m/c 4 | cutter setup | Administrative | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
23 | m/c 2 | Setup new hand scanner | Administrative | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
24 | m/c 3 | Grinder belt reset | Administrative | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
25 | m/c 4 | m/c 3 parameter checks | Administrative | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
26 | m/c 5 | Setup new hand scanner | Administrative | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
27 | m/c 6 | Change nitrogen bottle | Administrative | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
28 | m/c 7 | vibrationround stopping machine | Unplanned | Completed | L021 | 2016-11-30 | 2016-11-28 | 2016-11-28 | 2016-11-30
29 | m/c 5 | new wiring loom. | Unplanned | Completed | L108 | 2016-11-28 | 2016-11-27 | 2016-11-27 | 2016-11-28
30 | m/c 6 | grinder LHS and unblock. | Unplanned | Completed | L108 | 2016-11-28 | 2016-11-27 | 2016-11-27 | 2016-11-28
31 | m/c 7 | button broken off | Unplanned | Completed | L050 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26
32 | m/c 8 | stopping on | Unplanned | Completed | L067 | 2016-11-26 | 2016-11-25 | 2016-11-25 | 2016-11-26
33 | m/c 9 | hand scanner replaced | Unplanned | Completed | L021 | 2016-11-26 | 2016-11-25 | 2016-11-25 | 2016-11-26
34 | m/c 10 | closed sensor | Unplanned | Completed | L021 | 2016-11-28 | 2016-11-25 | 2016-11-25 | 2016-11-28
35 | m/c 3 | sealing unit | Improvement | Completed | L021 | 2016-11-28 | 2016-11-25 | 2016-11-25 | 2016-11-28
36 | m/c 4 | Changed over nitrogen bottle | Administrative | Completed | L021 | 2016-11-28 | 2016-11-25 | 2016-11-25 | 2016-11-28
37 | m/c 5 | vibrationround stopping machine | Improvement | Completed | L021 | 2016-11-28 | 2016-11-25 | 2016-11-25 | 2016-11-28
38 | m/c 6 | new wiring loom. | Administrative | Completed | L021 | 2016-11-28 | 2016-11-25 | 2016-11-25 | 2016-11-28
39 | m/c 7 | grinder LHS and unblock. | Unplanned | Completed | L021 | 2016-11-28 | 2016-11-25 | 2016-11-25 | 2016-11-28
40 | m/c 8 | button broken off | Other | Completed | L050 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24
41 | m/c 9 | stopping on | Administrative | Completed | L021 | 2016-11-26 | 2016-11-24 | 2016-11-24 | 2016-11-26
42 | m/c 6 | Change from silo 5 to 4 | Administrative | Completed | L021 | 2016-11-26 | 2016-11-24 | 2016-11-24 | 2016-11-26
43 | m/c 7 | Water hydraulics water top-up | Improvement | Completed | L021 | 2016-11-26 | 2016-11-24 | 2016-11-24 | 2016-11-26
44 | m/c 8 | vibrationround stopping machine | Unplanned | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
45 | m/c 9 | new wiring loom. | Improvement | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
46 | m/c 10 | grinder LHS and unblock. | Improvement | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
47 | m/c 11 | button broken off | Improvement | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
48 | m/c 12 | stopping on | Unplanned | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
49 | m/c 13 | initialise laser & brake test robot | Administrative | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
50 | m/c 14 | Pump holder loose | Improvement | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
51 | m/c 15 | cutting unit spinning continuously after cycle | Unplanned | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
52 | m/c 1 | Vent cutter still spinning after cutting | Unplanned | Completed | L021 | 2016-11-28 | 2016-11-24 | 2016-11-24 | 2016-11-28
53 | m/c 2 | m/1 down | Unplanned | Completed | L021 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
54 | m/c 3 | Nest prep ready for tool change | Administrative | Completed | L021 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
55 | m/c 4 | unit reset x 2 | Unplanned | Completed | L021 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
56 | m/c 5 | leak around the balloon area. | Improvement | Completed | L021 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
57 | m/c 6 | Nest change | Administrative | Completed | L021 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
58 | m/c 7 | All weld parameter checks | Administrative | Completed | L021 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
59 | m/c 8 | label printer on manual | Planned Repair | Completed | L119 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-25
60 | m/c 9 | Weekly test on Robot | Preventive Maintenance | Completed |  | 2016-11-18 | 2016-11-23 | 2016-11-24 | 2016-11-25
61 | m/c 10 | Weekly test on Robot | Preventive Maintenance | Completed |  | 2016-11-18 | 2016-11-23 | 2016-11-24 | 2016-11-25
62 | m/c 11 | Weekly test on Robot | Preventive Maintenance | Completed |  | 2016-11-18 | 2016-11-23 | 2016-11-24 | 2016-11-25
63 | m/c 12 | Weekly test on Robot | Preventive Maintenance | Completed |  | 2016-11-18 | 2016-11-23 | 2016-11-24 | 2016-11-25
59 | m/c 8 | label printer on manual | Planned Repair | Completed | L119 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-25
64 | m/c 13 | Weekly test on m/c | Improvement | Completed | L021 | 2016-11-26 | 2016-11-23 | 2016-11-23 | 2016-11-26
65 | m/c 14 | [Person_1] tests | Preventive Maintenance | Completed |  | 2016-11-22 | 2016-11-23 | 2016-11-29 | 2016-11-25
66 | m/c 15 | [Person_2] system | Preventive Maintenance | Completed |  | 2016-11-22 | 2016-11-23 | 2016-11-29 | 2016-11-25
67 | m/c 16 | Site [Person_3] and [Person_4] house ~ Conduct weekly sprinkler pump test and pump | Preventive Maintenance | Completed |  | 2016-11-22 | 2016-11-23 | 2016-11-29 | 2016-11-28
68 | m/c 17 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
69 | m/c 18 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
70 | m/c 19 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
71 | m/c 13 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
72 | m/c 14 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
73 | m/c 15 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
74 | m/c 16 | Weekly test on m/c | Preventive Maintenance | Completed | L108 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
75 | m/c 17 | missing nest 4. | Unplanned | Completed | L050 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
76 | m/c 18 | conveyor | Unplanned | Completed | L050 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
77 | m/c 19 | pipe couplings. etc. | Unplanned | Completed | [Person_5] | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
78 | m/c 20 | parameter checks | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
79 | m/c 21 | parameter checks | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
80 | m/c 22 | parameter checks | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
59 | m/c 8 | label printer on manual | Planned Repair | Completed | L119 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-25
81 | m/c 23 | parameter checks | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
82 | m/c 24 | Labels change | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
83 | m/c 25 | conveyor | Unplanned | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
84 | m/c 26 | Labels change | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
85 | m/c 27 | gripper reset & home | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
86 | m/c 28 | Laser initialisation | Administrative | Completed | L021 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
87 | m/c 29 | conveyor | Unplanned | Completed | L080 | 2016-11-22 | 2016-11-22 | 2016-11-29 | 2016-11-22
88 | m/c 30 | conveyor | Unplanned | Completed | [Person_5] | 2016-11-22 | 2016-11-21 | 2016-11-21 | 2016-11-22
89 | m/c 31 | pipe couplings. etc. | Unplanned | Completed |  | 2016-11-18 | 2016-11-21 | 2016-11-27 | 2016-11-28
90 | m/c 32 | parameter checks | Administrative | Completed |  | 2016-11-11 | 2016-11-21 | 2016-11-27 | 2016-11-29
91 | m/c 33 | parameter checks | Administrative | Completed | L108 | 2016-08-05 | 2016-11-21 | 2016-12-04 | 2016-11-21
92 | m/c 34 | parameter checks | Administrative | Completed |  | 2016-11-25 | 2016-11-21 | 2016-12-04 | 2016-11-25
93 | m/c 35 | EHS Ladders & Step Ladders | Preventive Maintenance | Completed |  | 2016-11-18 | 2016-11-21 | 2016-11-27 | 2016-11-25
94 | m/c 36 | EHS Ladders & Step Ladders | Preventive Maintenance | Completed |  | 2016-11-18 | 2016-11-21 | 2016-11-27 | 2016-11-25
95 | m/c 37 | conveyor | Unplanned | Completed |  | 2016-11-16 | 2016-11-21 | 2016-11-27 | 2016-11-25
96 | m/c 38 | pipe couplings. etc. | Unplanned | Completed |  | 2016-11-16 | 2016-11-21 | 2016-11-27 | 2016-11-25
97 | m/c 39 | parameter checks | Administrative | Completed |  | 2016-11-16 | 2016-11-21 | 2016-11-27 | 2016-11-25
98 | m/c 40 | parameter checks | Administrative | Completed | L119 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-21
59 | m/c 8 | label printer on manual | Planned Repair | Completed | L119 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-25
99 | m/c 41 | parameter checks | Administrative | Completed | L119 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-21
100 | m/c 42 | Weekly test on m/c | Preventive Maintenance | Completed | L119 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-21
101 | m/c 43 | Weekly test on m/c | Preventive Maintenance | Completed | L119 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-21
102 | m/c 44 | missing nest 4. | Unplanned | Completed | L108 | 2016-11-21 | 2016-11-20 | 2016-11-20 | 2016-11-21
103 | m/c 45 | conveyor | Unplanned | Completed | L108 | 2016-11-21 | 2016-11-20 | 2016-11-20 | 2016-11-21
104 | m/c 46 | pipe couplings. etc. | Unplanned | Completed | L092 | 2016-11-20 | 2016-11-19 | 2016-11-19 | 2016-11-20
105 | m/c 47 | Weekly test on m/c | Preventive Maintenance | Completed | L092 | 2016-11-20 | 2016-11-19 | 2016-11-19 | 2016-11-20
106 | m/c 48 | Weekly test on m/c | Preventive Maintenance | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
107 | m/c 49 | missing nest 4. | Unplanned | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
108 | m/c 50 | conveyor | Unplanned | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
109 | m/c 51 | pipe couplings. etc. | Unplanned | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
110 | m/c 52 | Deflash robot stopped | Unplanned | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
111 | m/c 53 | Replace print | Unplanned | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
112 | m/c 54 | Inspect chiller for leaks | Unplanned | Completed | [Person_5] | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
113 | m/c 55 | Deflash robot stopped | Unplanned | Completed | L030 | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
114 | m/c 56 | Weekly test on m/c | Preventive Maintenance | Completed | L092 | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
115 | m/c 57 | missing nest 4. | Unplanned | Completed | L092 | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
116 | m/c 58 | pipe couplings. etc. | Unplanned | Completed | L050 | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
117 | m/c 16 | Deflash robot stopped | Unplanned | Completed | L050 | 2016-11-18 | 2016-11-18 | 2016-11-18 | 2016-11-18
118 | m/c 17 | Replace print | Unplanned | Completed | L050 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17
119 | m/c 18 | Inspect chiller for leaks | Unplanned | Completed | L050 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17
120 | m/c 19 | 1N6 Part present intermittent. | Unplanned | Completed | L050 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 15:13
121 | m/c 20 | Slug stuck on pin | Unplanned | Completed | L050 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 15:13
122 | m/c 21 | replace sensor ring loader | Other | Completed | L050 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 15:13
123 | m/c 22 | Replaced bracket sensor | Unplanned | Completed | L021 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 15:13
124 | m/c 23 | Air leak from tank | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-17 | 2016-11-17 | 2016-11-18
125 | m/c 24 | Camera check issue | Administrative | Completed | L021 | 2016-11-18 | 2016-11-17 | 2016-11-17 | 2016-11-18
126 | m/c 18 | assist bracket assenbly | Improvement | Completed | L021 | 2016-11-18 | 2016-11-17 | 2016-11-17 | 2016-11-18
127 | m/c 19 | Tank detaching | Administrative | Completed | L021 | 2016-11-18 | 2016-11-17 | 2016-11-17 | 2016-11-18
128 | m/c 20 | Set-up tank clamp, improve | Improvement | Completed | L021 | 2016-11-18 | 2016-11-17 | 2016-11-17 | 2016-11-18
129 | m/c 21 | material alarms | Administrative | Completed | L021 | 2016-11-18 | 2016-11-17 | 2016-11-17 | 2016-11-18
130 | m/c 22 | Camera check issue | Administrative | Completed | L121 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
131 | m/c 23 | assist bracket assenbly | Improvement | Completed | L029 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
132 | m/c 24 | Tank detaching | Administrative | Completed | L029 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
133 | m/c 25 | Set-up tank clamp, improve | Improvement | Completed | L050 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-17
134 | m/c 26 | material alarms | Administrative | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
135 | m/c 27 | Inspect chiller for leaks | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
136 | m/c 28 | Deflash robot stopped | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
137 | m/c 29 | Weekly test on m/c | Preventive Maintenance | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
138 | m/c 30 | missing nest 4. | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
139 | m/c 31 | pipe couplings. etc. | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
59 | m/c 8 | label printer on manual | Planned Repair | Completed | L119 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-25
140 | m/c 32 | Deflash robot stopped | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-16 | 2016-11-16 | 2016-11-18
141 | m/c 33 | Replace print | Unplanned | Completed |  | 2016-11-18 | 2016-11-16 | 2016-11-17 | 2016-11-18
142 | m/c 34 | Inspect chiller for leaks | Unplanned | Completed |  | 2016-11-18 | 2016-11-16 | 2016-11-17 | 2016-11-18
143 | m/c 35 | 1N6 Part present intermittent. | Unplanned | Completed |  | 2016-11-18 | 2016-11-16 | 2016-11-17 | 2016-11-18
144 | m/c 36 | Slug stuck on pin | Unplanned | Completed |  | 2016-11-18 | 2016-11-16 | 2016-11-17 | 2016-11-18
145 | m/c 37 | replace sensor ring loader | Other | Completed |  | 2016-11-15 | 2016-11-16 | 2016-11-22 | 2016-11-22
146 | m/c 38 | Replaced bracket sensor | Unplanned | Completed |  | 2016-11-15 | 2016-11-16 | 2016-11-22 | 2016-11-22
147 | m/c 39 | Replaced bracket sensor | Unplanned | Completed |  | 2016-11-15 | 2016-11-16 | 2016-11-22 | 2016-11-22
148 | m/c 40 | Air leak from tank | Unplanned | Completed | L121 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
149 | m/c 41 | Camera check issue | Administrative | Completed | L021 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
150 | m/c 42 | assist bracket assenbly | Improvement | Completed | L021 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
151 | m/c 43 | Tank detaching | Administrative | Completed | L021 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
152 | m/c 44 | Set-up tank clamp, improve | Improvement | Completed | L021 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
153 | m/c 45 | material alarms | Administrative | Completed | L021 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
154 | m/c 46 | Camera check issue | Administrative | Completed | L121 | 2016-11-16 | 2016-11-15 | 2016-11-15 | 2016-11-16
155 | m/c 47 | assist bracket assenbly | Improvement | Completed | L121 | 2016-11-16 | 2016-11-15 | 2016-11-15 | 2016-11-16
156 | m/c 48 | Robot struggling to take tank from top of CF2 | Improvement | Completed | L121 | 2016-11-16 | 2016-11-15 | 2016-11-15 | 2016-11-16
157 | m/c 49 | Water hydraulics top-up | Administrative | Completed | L021 | 2016-11-18 | 2016-11-15 | 2016-11-15 | 2016-11-18
158 | m/c 50 | Nests not turning, bearing sticking | Unplanned | Completed | L021 | 2016-11-18 | 2016-11-15 | 2016-11-15 | 2016-11-18
159 | m/c 51 | Start-up | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
160 | m/c 52 | Topped up hydraulics with water x 2 | Unplanned | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
161 | m/c 53 | missing nest 4. | Unplanned | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
162 | m/c 54 | conveyor | Unplanned | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
163 | m/c 55 | pipe couplings. etc. | Unplanned | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
164 | m/c 56 | parameter checks | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
165 | m/c 57 | parameter checks | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
166 | m/c 58 | parameter checks | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
167 | m/c 4 | parameter checks | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
168 | m/c 5 | Labels change | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
169 | m/c 6 | conveyor | Unplanned | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
170 | m/c 7 | Labels change | Administrative | Completed | L021 | 2016-11-15 | 2016-11-14 | 2016-11-14 | 2016-11-15
171 | m/c 8 | gripper reset & home | Administrative | Cancelled | L021 | 2016-11-15 | 2016-11-14 | 2016-11-15 | 2016-11-17
172 | m/c 9 | Laser initialisation | Administrative | Completed |  | 2016-08-08 | 2016-11-14 | 2016-11-20 | 2016-11-22
173 | m/c 10 | conveyor | Unplanned | Completed |  | 2016-09-09 | 2016-11-14 | 2016-11-20 | 2016-11-25
174 | m/c 11 | conveyor | Unplanned | Completed |  | 2016-10-17 | 2016-11-14 | 2016-11-27 | 2016-11-28
175 | m/c 12 | pipe couplings. etc. | Unplanned | Completed |  | 2016-09-30 | 2016-11-14 | 2016-11-27 | 2016-11-30
176 | m/c 13 | parameter checks | Administrative | Completed |  | 2016-08-06 | 2016-11-14 | 2016-11-27 | 2016-11-30
177 | m/c 14 | Inspect chiller for leaks | Unplanned | Completed |  | 2016-10-12 | 2016-11-14 | 2016-11-20 | 2016-12-01
178 | m/c 15 | 1N6 Part present intermittent. | Unplanned | Completed |  | 2016-09-09 | 2016-11-14 | 2016-11-20 | 2016-12-01
179 | m/c 11 | Slug stuck on pin | Unplanned | Completed |  | 2016-11-16 | 2016-11-14 | 2016-11-20 | 2016-11-16
180 | m/c 12 | replace sensor ring loader | Other | Completed |  | 2016-11-16 | 2016-11-14 | 2016-11-20 | 2016-11-16
181 | m/c 13 | Replaced bracket sensor | Unplanned | Cancelled | L014 | 2016-11-14 | 2016-11-14 | 2016-11-18 | 2016-11-17
182 | m/c 14 | Replaced bracket sensor | Unplanned | Completed |  | 2016-10-24 | 2016-11-14 | 2016-11-27 | 2016-11-18
183 | m/c 15 | Air leak from tank | Unplanned | Completed |  | 2016-11-18 | 2016-11-14 | 2016-11-20 | 2016-11-18
184 | m/c 16 | Camera check issue | Administrative | Completed | L050 | 2016-11-14 | 2016-11-13 | 2016-11-13 | 2016-11-13
185 | m/c 17 | assist bracket assenbly | Improvement | Completed | L119 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-14
186 | m/c 18 | Tank detaching | Administrative | Completed | L050 | 2016-11-14 | 2016-11-13 | 2016-11-13 | 2016-11-14
187 | m/c 19 | Set-up tank clamp, improve | Improvement | Completed | L119 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-15
188 | m/c 20 | material alarms | Administrative | Completed | [Person_5] | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-11
189 | m/c 21 | Camera check issue | Administrative | Completed | [Person_5] | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-11
190 | m/c 22 | assist bracket assenbly | Improvement | Completed | [Person_5] | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-11
191 | m/c 23 | Ultrasonic sensors failed | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-11
192 | m/c 24 | Replaced pump present sensor | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-11
193 | m/c 25 | Cooling pump tripped out | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-11
194 | m/c 26 | M/c stop | Unplanned | Completed | L092 | 2016-11-12 | 2016-11-11 | 2016-11-11 | 2016-11-12
195 | m/c 27 | proving unit project | Other | Cancelled | L050 | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-17
196 | m/c 28 | Camera check issue | Administrative | Cancelled | L122 | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-17
197 | m/c 29 | assist bracket assenbly | Improvement | Completed | L050 | 2016-11-11 | 2016-11-11 | 2016-11-11 | 2016-11-10
198 | m/c 30 | Ultrasonic sensors failed | Unplanned | Completed | L029 | 2016-11-12 | 2016-11-10 | 2016-11-10 | 2016-11-10
199 | m/c 31 | Replaced pump present sensor | Unplanned | Completed | L029 | 2016-11-12 | 2016-11-10 | 2016-11-10 | 2016-11-10
200 | m/c 32 | Cooling pump tripped out | Unplanned | Completed | L050 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-10
201 | m/c 33 | M/c stop | Unplanned | Completed | L050 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-11
202 | m/c 34 | proving unit project | Other | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
203 | m/c 35 | Laser initialisation | Administrative | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
204 | m/c 36 | conveyor | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
205 | m/c 37 | conveyor | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
206 | m/c 38 | pipe couplings. etc. | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
207 | m/c 39 | parameter checks | Administrative | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
208 | m/c 40 | Inspect chiller for leaks | Unplanned | Completed | L108 | 2016-11-11 | 2016-11-10 | 2016-11-10 | 2016-11-11
209 | m/c 41 | 1N6 Part present intermittent. | Unplanned | Cancelled | L115 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-17
210 | m/c 42 | Slug stuck on pin | Unplanned | Completed | L050 | 2016-11-11 | 2016-11-10 | 2016-11-11 | 2016-11-10
211 | m/c 43 | replace sensor ring loader | Other | Completed | L029 | 2016-11-12 | 2016-11-09 | 2016-11-09 | 2016-11-09
212 | m/c 44 | Replaced bracket sensor | Unplanned | Completed | L029 | 2016-11-12 | 2016-11-09 | 2016-11-09 | 2016-11-09
213 | m/c 22 | Replaced bracket sensor | Unplanned | Completed | L050 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
214 | m/c 23 | Air leak from tank | Unplanned | Completed | L050 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
215 | m/c 24 | Camera check issue | Administrative | Completed | L049 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
216 | m/c 25 | assist bracket assenbly | Improvement | Completed | L021 | 2016-11-15 | 2016-11-09 | 2016-11-09 | 2016-11-15
217 | m/c 26 | Tank detaching | Administrative | Completed | L021 | 2016-11-15 | 2016-11-09 | 2016-11-09 | 2016-11-15
218 | m/c 27 | Set-up tank clamp, improve | Improvement | Completed | L021 | 2016-11-15 | 2016-11-09 | 2016-11-09 | 2016-11-15
219 | m/c 28 | material alarms | Administrative | Completed | L021 | 2016-11-15 | 2016-11-09 | 2016-11-09 | 2016-11-15
220 | m/c 29 | Camera check issue | Administrative | Completed | L021 | 2016-11-15 | 2016-11-09 | 2016-11-09 | 2016-11-15
221 | m/c 30 | assist bracket assenbly | Improvement | Completed |  | 2016-11-08 | 2016-11-09 | 2016-11-15 | 2016-11-15
222 | m/c 31 | Ultrasonic sensors failed | Unplanned | Completed |  | 2016-11-08 | 2016-11-09 | 2016-11-15 | 2016-11-15
223 | m/c 32 | Replaced pump present sensor | Unplanned | Completed |  | 2016-11-08 | 2016-11-09 | 2016-11-15 | 2016-11-15
224 | m/c 33 | Cooling pump tripped out | Unplanned | Completed |  | 2016-11-02 | 2016-11-09 | 2016-11-10 | 2016-11-18
225 | m/c 34 | M/c stop | Unplanned | Completed |  | 2016-11-02 | 2016-11-09 | 2016-11-10 | 2016-11-18
226 | m/c 35 | proving unit project | Other | Completed |  | 2016-11-02 | 2016-11-09 | 2016-11-10 | 2016-11-18
227 | m/c 36 | Camera check issue | Administrative | Completed |  | 2016-11-02 | 2016-11-09 | 2016-11-10 | 2016-11-18
228 | m/c 37 | assist bracket assenbly | Improvement | Completed | L125 | 2016-11-09 | 2016-11-09 | 2016-11-11 | 2016-11-09
229 | m/c 38 | Ultrasonic sensors failed | Unplanned | Completed | L095 | 2016-11-09 | 2016-11-09 | 2016-11-30 | 2016-11-25
230 | m/c 39 | Replaced pump present sensor | Unplanned | Completed | L050 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
231 | m/c 4 | Cooling pump tripped out | Unplanned | Completed | L050 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
232 | m/c 5 | M/c stop | Unplanned | Completed | L067 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 15:31
233 | m/c 6 | proving unit project | Other | Completed | L050 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
234 | m/c 7 | M/c stop | Unplanned | Completed | L050 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
235 | m/c 8 | proving unit project | Other | Completed | L050 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
236 | m/c 9 | Camera check issue | Administrative | Completed | L029 | 2016-11-12 | 2016-11-08 | 2016-11-08 | 2016-11-08
237 | m/c 10 | assist bracket assenbly | Improvement | Completed | L029 | 2016-11-12 | 2016-11-08 | 2016-11-08 | 2016-11-08
238 | m/c 11 | Ultrasonic sensors failed | Unplanned | Completed | L021 | 2016-11-10 | 2016-11-08 | 2016-11-08 | 2016-11-10
239 | m/c 12 | Replaced pump present sensor | Unplanned | Completed | L021 | 2016-11-10 | 2016-11-08 | 2016-11-08 | 2016-11-10
240 | m/c 13 | Cooling pump tripped out | Unplanned | Completed | L115 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-10
241 | m/c 14 | Unload robot dropped | Administrative | Completed | L021 | 2016-11-10 | 2016-11-08 | 2016-11-08 | 2016-11-10
242 | m/c 8 | Station 2, faulting | Unplanned | Completed | L021 | 2016-11-10 | 2016-11-08 | 2016-11-08 | 2016-11-10
243 | m/c 9 | [Person_6] opened up | Improvement | Completed | L021 | 2016-11-10 | 2016-11-08 | 2016-11-08 | 2016-11-10
244 | m/c 10 | Camera check issue | Administrative | Cancelled | L122 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-17
245 | m/c 11 | assist bracket assenbly | Improvement | Completed | L021 | 2016-11-09 | 2016-11-07 | 2016-11-07 | 2016-11-09
246 | m/c 12 | Ultrasonic sensors failed | Unplanned | Completed | L115 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-09
247 | m/c 13 | Replaced pump present sensor | Unplanned | Completed | L021 | 2016-11-09 | 2016-11-07 | 2016-11-07 | 2016-11-09
248 | m/c 14 | Cooling pump tripped out | Unplanned | Completed | L021 | 2016-11-09 | 2016-11-07 | 2016-11-07 | 2016-11-09
249 | m/c 15 | M/c stop | Unplanned | Completed | L021 | 2016-11-09 | 2016-11-07 | 2016-11-07 | 2016-11-09
250 | m/c 16 | proving unit project | Other | Completed | L021 | 2016-11-09 | 2016-11-07 | 2016-11-07 | 2016-11-09
251 | m/c 17 | Camera check issue | Administrative | Completed | L021 | 2016-11-09 | 2016-11-07 | 2016-11-07 | 2016-11-09
252 | m/c 18 | assist bracket assenbly | Improvement | Completed | L021 | 2016-11-10 | 2016-11-07 | 2016-11-07 | 2016-11-10
253 | m/c 19 | Ultrasonic sensors failed | Unplanned | Completed | L021 | 2016-11-10 | 2016-11-07 | 2016-11-07 | 2016-11-10
254 | m/c 20 | Replaced pump present sensor | Unplanned | Completed | L120 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-14
255 | m/c 9 | Cooling pump tripped out | Unplanned | Completed |  | 2016-11-16 | 2016-11-07 | 2016-11-13 | 2016-11-16
256 | m/c 10 | M/c stop | Unplanned | Completed |  | 2016-11-16 | 2016-11-07 | 2016-11-13 | 2016-11-16
257 | m/c 11 | proving unit project | Other | Cancelled | L119 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-17
258 | m/c 12 | M/c stop | Unplanned | Completed |  | 2016-11-16 | 2016-11-07 | 2016-11-13 | 2016-11-18
259 | m/c 13 | proving unit project | Other | Completed |  | 2016-11-02 | 2016-11-07 | 2016-11-13 | 2016-11-18
260 | m/c 14 | Camera check issue | Administrative | Completed |  | 2016-11-01 | 2016-11-07 | 2016-11-13 | 2016-11-18
261 | m/c 15 | assist bracket assenbly | Improvement | Completed |  | 2016-09-30 | 2016-11-07 | 2016-11-20 | 2016-11-22
262 | m/c 16 | Ultrasonic sensors failed | Unplanned | Completed |  | 2016-11-22 | 2016-11-07 | 2016-11-13 | 2016-11-22
263 | m/c 17 | Replaced pump present sensor | Unplanned | Completed |  | 2016-11-22 | 2016-11-07 | 2016-11-13 | 2016-11-22
264 | m/c 18 | Cooling pump tripped out | Unplanned | Completed |  | 2016-10-09 | 2016-11-07 | 2016-11-13 | 2016-11-25
265 | m/c 19 | Unload robot dropped | Administrative | Completed |  | 2016-10-13 | 2016-11-07 | 2016-11-13 | 2016-11-25
266 | m/c 20 | Station 2, faulting | Unplanned | Completed |  | 2016-11-30 | 2016-11-07 | 2016-11-13 | 2016-11-30
267 | m/c 21 | [Person_6] opened up | Improvement | Completed |  | 2016-11-21 | 2016-11-07 | 2016-11-20 | 2016-11-30
268 | m/c 22 | Change filters | Preventive Maintenance | Completed |  | 2016-11-06 | 2016-11-07 | 2016-11-13 | 2016-11-06
269 | m/c 23 | [Person_7] | Preventive Maintenance | Completed |  | 2016-09-30 | 2016-11-07 | 2016-11-20 | 2016-11-18
270 | m/c 24 | Camera check not working. | Unplanned | Completed | L050 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
271 | m/c 25 | Moulding Tool 1 | Unplanned | Completed | [Person_5] | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
272 | m/c 26 | Moulding Tool 2 | Unplanned | Completed | [Person_5] | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
273 | m/c 27 | Moulding Tool 3 | Administrative | Completed | L031 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
274 | m/c 28 | Head clean Line 1 | Improvement | Completed | L021 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
275 | m/c 29 | tool change prep | Unplanned | Completed | L021 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
276 | m/c 11 | setpoints defaulted had to setup again. | Unplanned | Completed | L021 | 2016-11-09 | 2016-11-06 | 2016-11-06 | 2016-11-09
277 | m/c 12 | M/c start | Administrative | Completed | L021 | 2016-11-09 | 2016-11-06 | 2016-11-06 | 2016-11-09
278 | m/c 13 | Needle temperature | Unplanned | Completed | L021 | 2016-11-09 | 2016-11-06 | 2016-11-06 | 2016-11-09
279 | m/c 14 | Will not start m/c 1 | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
280 | m/c 15 | rewire sensors | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
281 | m/c 16 | grinder stopped | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
282 | m/c 17 | force welding not reached | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
283 | m/c 18 | grinder stopped interlock not made. | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
284 | m/c 19 | tool change prep | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
285 | m/c 20 | laser problems | Unplanned | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
286 | m/c 21 | cutter setup | Administrative | Completed | L108 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
287 | m/c 22 | Setup new hand scanner | Administrative | Completed | L050 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
288 | m/c 23 | Grinder belt reset | Administrative | Completed | L050 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
289 | m/c 24 | m/c 3 parameter checks | Administrative | Completed | L050 | 2016-11-06 | 2016-11-05 | 2016-11-06 | 2016-11-06
290 | m/c 25 | Setup new hand scanner | Administrative | Completed | L050 | 2016-11-06 | 2016-11-05 | 2016-11-06 | 2016-11-06
291 | m/c 26 | Change nitrogen bottle | Administrative | Completed | [Person_5] | 2016-11-06 | 2016-11-05 | 2016-11-05 | 2016-11-06
292 | m/c 27 | vibrationround stopping machine | Unplanned | Completed | L048 | 2016-11-09 | 2016-11-05 | 2016-11-05 | 2016-11-09
293 | m/c 28 | new wiring loom. | Unplanned | Cancelled | L119 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-17
294 | m/c 29 | grinder LHS and unblock. | Unplanned | Cancelled | L119 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-17
295 | m/c 30 | button broken off | Unplanned | Completed | L119 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-23
296 | m/c 31 | stopping on | Unplanned | Completed | L119 | 2016-11-04 | 2016-11-04 | 2016-11-04 | 2016-11-14
297 | m/c 32 | hand scanner replaced | Unplanned | Completed | L001 | 2016-11-04 | 2016-11-04 | 2016-11-04 | 2016-11-23
298 | m/c 33 | Setup new hand scanner | Administrative | Cancelled | L122 | 2016-11-04 | 2016-11-04 | 2016-11-30 | 2016-11-28
299 | m/c 34 | Change nitrogen bottle | Administrative | Completed | L108 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
300 | m/c 35 | vibration around stopping machine | Unplanned | Completed | L108 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
301 | m/c 36 | Tool change | Unplanned | Completed | L108 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
59 | m/c 8 | label printer on manual | Planned Repair | Completed | L119 | 2016-11-23 | 2016-11-23 | 2016-11-23
Formulas:
Column1 = WEEKNUM([Sched. Start Date])
Week Closed = WEEKNUM([Date Completed])